## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Data Analytics
INTERN NAME: | Riswan Pk
PROJECT NAME: | Data Insights On Interns
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2024-03-21
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | DATA ANALYSIS INSIGHTS |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | IAC IP23 - LP
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2024-03-10 | Technical issue with data integration | Data Analysis | Yes | Invest in more robust data integration tools | IT Specialist assigned to research and propose alternative tools. | Data Analyst, IT Specialist | PENDING | Data analysis paused until issue resolved.
2 | 2024-03-16 | Data loss due to system failure | Data Management | Yes | Implement regular backups and data recovery procedures. | Restored data from the most recent backup. | IT Specialist | SOLVED | Investigating root cause to prevent future occurrences.
3 | 2024-03-25 | System downtime during critical analysis phase | Technical | Yes | Invest in redundant systems or backup servers to minimize downtime. | IT team conducted emergency maintenance and restored system functionality. | IT Specialist | SOLVED | Implementing measures to enhance system resilience.
4 | 2024-04-01 | Insufficient engagement from interns in feedback sessions | Stakeholder Engagement | Yes | Implement incentives for intern participation in feedback sessions and enhance communication about the importance of their input. | Introduced rewards for active participation in feedback sessions and communicated the value of their input in shaping the project. | HR Coordinator, Project Manager | SOLVED | Increased participation and valuable insights gained from intern feedback.